## 📋 Functional Requirements
FUNCTIONAL REQUIREMENTS MASTER ¦ D365 → ODOO 17 ¦ Port Said Governorate (الديوان العام لمحافظة بورسعيد)
Source Documents: FRD Supply Chain – Procurement (36pp) ¦ FRD Supply Chain – Inventory (24pp) ¦ User Guide Procurement (70pp) ¦ User Guide Inventory (17pp) ¦ FDD Procurement & Inventory (22pp)
Module | Req ID | Requirement Name (AR) | Requirement Name (EN) | Input Documents | Output Documents | D365 F&O Screen Path | Odoo 17 Target | Gap Type | Customization Ref | Priority | UAT Scenario ID
PROCUREMENT — التعاقدات
Procurement | PR-01 | العمليات التعاقدية الأولية | Initial Contracting Operations | مذكرة عرض الاحتياجات / طلب الاحتياج المقدم | أمر توريد، كراسة الشروط، قرار تشكيل اللجان | Procurement > Purchase agreements > Contracts | purchase.order / purchase.requisition | Custom | C5, C-PR01 | CRITICAL | UAT-PR-01
Procurement | PR-02 | المناقصة العامة للتوريدات | Public Tender – Supplies & Services | مذكرة الطرح على السلطة المختصة | نموذج حصر الشركات، كراسة الشروط، محضر فتح المظاريف، نموذج حصر العطاءات، محضر البت الفني أ/ب، محضر البت المالي 1/2، إخطار الترسية، تحرير عقد، أمر توريد، استمارة صرف | Procurement > RFQ > Vendor selection workflow | purchase.rfq + custom tender workflow | Custom | C-PR02 | CRITICAL | UAT-PR-02
Procurement | PR-03 | المناقصة المحلية/المحدودة للتوريدات | Local/Limited Tender – Supplies | مذكرة الطرح على السلطة المختصة | نموذج حصر الشركات، كراسة الشروط، كشف استلام العينات، نموذج حصر العطاءات، محضر البت الفني، محضر البت المالي، إخطار الترسية، عقد، أمر توريد، استمارة صرف | Procurement > RFQ > Limited vendor list | purchase.rfq + custom limited tender | Custom | C-PR03 | HIGH | UAT-PR-03
Procurement | PR-04 | الأمر المباشر / الاتفاق المباشر للتوريدات | Direct Order – Supplies & Services | مذكرة الطرح على السلطة المختصة | قرار تشكيل اللجان، كراسة الشروط، استمارة صرف 50 ع.ح، محضر الفحص الفني، محضر البت، إخطار الترسية، عقد، أمر التوريد | Procurement > Purchase orders > Direct agreement | purchase.order + custom approval bypass | Custom | C-PR04 | HIGH | UAT-PR-04
Procurement | PR-05 | المناقصة المحدودة/المحلية للمقاولات | Limited/Local Tender – Contracting Works | مذكرة الجهة الطالبة | مذكرة إدارة التعاقدات، كراسة الشروط، تقرير البت الفني، تقرير البت المالي، أمر الإسناد، عقد التنفيذ | Procurement > Subcontracting > Tender | purchase.order (subcontract) + custom | Custom | C-PR05 | HIGH | UAT-PR-05
Procurement | PR-06 | الأمر المباشر للمقاولات – شركات خاصة | Direct Order – Contracting (Private Firms) | مذكرة الجهة الطالبة | مذكرة إدارة التعاقدات، قرار تشكيل اللجان، كراسة الشروط، تقرير البت الفني، أمر إسناد، عقد التنفيذ، قرار الترسية | Procurement > Direct contracting | purchase.order + custom contracting module | Custom | C-PR06 | HIGH | UAT-PR-06
Procurement | PR-07 | الأمر المباشر للمقاولات – جهات سيادية | Direct Order – Contracting (Sovereign Entities) | مذكرة الجهة الطالبة | مذكرة إدارة التعاقدات، كراسة الشروط، أمر إسناد، عقد التنفيذ، تقرير البت الفني، قرار الترسية | Procurement > Sovereign entity contracting | purchase.order + sovereign entity flag | Custom | C-PR07 | HIGH | UAT-PR-07
Procurement | PR-08 | الطرح بوسيلة الممارسة | Negotiation / Practice Tender | مذكرة الطرح على السلطة المختصة | نموذج حصر الشركات، كراسة الشروط، محضر فتح المظاريف، كشف استلام العينات، نموذج حصر العطاءات، محضر البت الفني، محضر البت المالي، إخطار الترسية، عقد، أمر توريد، استمارة صرف | Procurement > Negotiation tender | purchase.rfq + negotiation workflow | Custom | C-PR08 | MEDIUM | UAT-PR-08
Procurement | PR-09 | الطرح بوسيلة المزايدة | Auction / Competitive Bidding | مذكرة الطرح على السلطة المختصة | نموذج حصر الشركات، كراسة الشروط، محضر فتح المظاريف المغلقة، نموذج حصر العطاءات، محضر البت المالي، إخطار الترسية، عقد | Procurement > Auction management | custom auction module | Custom | C-PR09 | MEDIUM | UAT-PR-09
INVENTORY — إدارة المخازن
Inventory | INV-01 | إذن الإضافة – استلام المخزون | Goods Receipt / Stock Addition Permit | أمر التوريد من إدارة المشتريات، فاتورة / شهادة إدارية | إذن إضافة (نموذج 1 مخازن) | التدبير وتحديد الموارد > أوامر الشراء > استلام > إيصال استلام منتجات مبدئي > محضر الفحص ¦ إدارة المخزون > إدخالات دفتر اليومية > وصول صنف | stock.picking (receipt) + quality.check | Config | — | CRITICAL | UAT-INV-01
Inventory | INV-02 | إذن الصرف | Stock Issue / Dispatch Permit | طلب إذن صرف | إذن صرف (مستديم/مستهلك) – نوع العهدة: فرعية/مكانية | إدارة المخزون > إدخالات دفتر اليومية > الحركة > اذن صرف > اختيار الصنف ونوعه والعامل/الإدارة | stock.picking (internal) + asset custody | Custom | C12, C-INV02 | CRITICAL | UAT-INV-02
Inventory | INV-03 | إذن الارتجاع | Stock Return / Rejection Permit | تقرير لجنة الارتجاع (لجنة الفحص) نموذج 8 مخازن | بيع الأصناف الكهنة – كشف حصر بالأصناف المستغني عنها | إدارة المخزون > إدخالات دفتر اليومية > الحركة > اذن ارتجاع | stock.picking (return) + scrap.order | Config | — | HIGH | UAT-INV-03
Inventory | INV-04 | العهدة الشخصية | Personal Asset Custody (استمارة 193 ع.ح) | إذن صرف عهدة – استمارة 193 ع.ح | صرف عهد شخصية – كشف عهدة (نموذج 1 مخازن) – نقل عهدة بين موظفين | إدارة المخزون > العهد > عهد مخزنية > نقل عهدة | stock.quant + hr.employee (custom custody) | Custom | C12, C-INV04 | CRITICAL | UAT-INV-04
Inventory | INV-05 | الجرد الدوري | Periodic Physical Stocktake (نموذج 6 مخازن) | نموذج 6 مخازن حكومية | بيان موجودات – محضر جرد أصناف (نموذج 6 مخازن) – كشف الزيادة والعجز | إدارة المخزون > جرد > الأصناف > الجرد ¦ تحديد الصنف والمخزن وإدخال الرقم الفعلي ثم ترحيل | stock.inventory (Odoo 17: stock.quant adjustment) | Config | — | HIGH | UAT-INV-05
Inventory | INV-06 | المخزون الراكد | Slow-Moving / Dead Stock Management | بيان مخزون الراكد | تصريح بالبيع – محضر إجراءات بيع أصناف – مقايسة مستلزمات سلعية | Inventory > Reports > Inventory aging / dead stock | stock.quant + custom slow-moving report | Custom | C-INV06 | HIGH | UAT-INV-06
Inventory | INV-07 | أرباب العهدة – التأمين الحكومي | Asset Custodian Insurance (Gov't Obligation) | كشف عهد | سداد مستحقات الحكومة تجاه التأمين على أرباب العهد – مستند صرف التأمينات الاجتماعية | N/A in D365 — manual process currently | custom insurance obligation module | Custom | C-INV07 | MEDIUM | UAT-INV-07
GOVERNMENT FORMS INDEX ¦ نماذج حكومية مرجعية — الديوان العام لمحافظة بورسعيد
Form No. | Arabic Name | English Name | Linked Req. | Odoo 17 Implementation Approach
نموذج 1 مخازن | إذن إضافة | Stock Addition Permit | INV-01, INV-04 | Odoo: stock.picking receipt + custom print layout (Arabic RTL)
نموذج 4 مخازن | دفتر شطب | Write-off Register | INV-03 | Odoo: scrap.order + custom report
نموذج 5 مخازن | يومية المخزن | Daily Warehouse Journal | INV-01/02/03 | Odoo: stock.move daily report (custom)
نموذج 6 مخازن | محضر جرد أصناف | Physical Inventory Count Minutes | INV-05 | Odoo: stock.inventory adjustment + custom Arabic minutes report
نموذج 8 مخازن | طلب ارتجاع أصناف | Return Items Request | INV-03 | Odoo: stock.picking return + نموذج 8 Arabic print
نموذج 9 مخازن | كشف الأصناف التالفة/المفقودة | Damaged/Missing Items List | INV-05 | Odoo: scrap.order + custom loss report
استمارة 193 ع.ح | إذن صرف عهدة | Personal Custody Dispatch Form | INV-02, INV-04 | Odoo: custom custody.move model + استمارة 193 print
استمارة صرف 50 ع.ح | استمارة صرف مباشر | Direct Payment/Disbursement Form | PR-04 | Odoo: account.payment + custom gov't form
محضر البت الفني | قرار اللجنة الفنية | Technical Committee Decision Minutes | PR-02–PR-08 | Odoo: custom tender.committee.minutes model
إخطار الترسية | إشعار الترسية للمورد الفائز | Award Notification | PR-02–PR-09 | Odoo: purchase.order + custom award letter template
كراسة الشروط والمواصفات | وثيقة المناقصة | Tender Specifications Document | PR-02–PR-09 | Odoo: custom tender.document model attached to RFQ

## 🔍 Gap Analysis
GAP ANALYSIS ¦ D365 F&O vs ODOO 17 ¦ Procurement & Inventory Modules ¦ Port Said Governorate
Req ID | D365 F&O Capability | Odoo 17 Standard Coverage | Gap Description | Classification | Custom Module | Est. Hours | Impact | Workaround Available? | Decision
PR-01 | Full contract lifecycle management: initial needs memo, committee formation, tender docs, award, PO | purchase.order + purchase.agreement. No government tender committee workflow. | Missing: committee decision workflow, Arabic government document templates (كراسة الشروط، قرار التشكيل), multi-stage approval per Egyptian procurement law | Custom | C-PR01 | 60 | CRITICAL | No | Build custom tender.lifecycle module
PR-02 | Public tender (مناقصة عامة): vendor shortlisting, sealed bids, technical committee, financial committee, award notice | No public tender workflow in Odoo 17 standard | Full tender management pipeline missing: bid opening (فتح المظاريف), technical evaluation (البت الفني), financial evaluation (البت المالي), award notification (إخطار الترسية) | Custom | C-PR02 | 80 | CRITICAL | No | Build procurement.tender module with full pipeline
PR-03 | Limited/local tender: pre-qualified vendor list, specifications, sample receipt, evaluation | purchase.rfq with vendor list partially covers | Missing: sample receipt register (كشف استلام العينات), limited vendor registry, Arabic tender announcements (صورة الإعلان) | Custom | C-PR03 | 45 | HIGH | Partial | Extend purchase.rfq + add custom models
PR-04 | Direct order: simplified committee, technical inspection, form 50 disbursement | purchase.order direct creation. No gov't form output. | Missing: استمارة صرف 50 ع.ح print, technical inspection minutes (محضر الفحص الفني), simplified committee decision | Custom | C-PR04 | 30 | HIGH | No | Extend PO with custom Arabic print templates
PR-05/06/07 | Contracting works tendering: subcontract award (أمر إسناد), execution contract, technical report | mrp.subcontracting partially. No tender for works. | Missing: works-specific tender pipeline, أمر إسناد document, sovereign entity flag for PR-07, different approval authority per entity type | Custom | C-PR05/06/07 | 70 | HIGH | No | Extend custom tender module for contracting type
PR-08 | Negotiation tender (ممارسة): similar to limited tender with negotiation stage | No negotiation tender in standard | Missing negotiation stage between technical and financial evaluation | Custom | C-PR08 | 25 | MEDIUM | Partial | Add negotiation stage to tender module
PR-09 | Auction (مزايدة): sealed bids, highest bidder wins (reverse of tender) | No auction in standard Odoo | Auction logic is inverse of procurement tender — highest price wins. Completely custom. | Custom | C-PR09 | 35 | MEDIUM | No | Separate auction module or extend tender with auction type flag
INV-01 | Goods receipt via PO → product receipt voucher → quality inspection → إذن إضافة (نموذج 1) | stock.picking receipt + quality.check module covers most | Minor gap: Arabic إذن إضافة print (نموذج 1 مخازن) not standard. Quality check required before addition. | Config | — | 8 | CRITICAL | Yes | Configure stock + quality; custom نموذج 1 print layout
INV-02 | Stock issue: permanent (مستديم) vs consumable (مستهلك), custody type: sub (فرعية) / location (مكانية), assigned to employee/department | stock.picking internal moves partially. No custody tracking. | Missing: item type classification (مستديم/مستهلك), custody type (فرعية/مكانية), employee assignment on move line, Arabic إذن صرف print | Custom | C12, C-INV02 | 45 | CRITICAL | No | Extend stock.move with custody fields; custom إذن صرف
INV-03 | Returns: inspection committee report (نموذج 8), surplus item disposal, scrap/sale of old items | stock.return + scrap.order covers base | Missing: نموذج 8 مخازن print, inspection committee workflow (لجنة الفحص), sale authorization for disposed items | Config | — | 12 | HIGH | Partial | Configure return + scrap; add نموذج 8 Arabic print
INV-04 | Personal custody (عهدة): issue to named employee via استمارة 193 ع.ح, custody transfer between employees, custody register | No employee custody tracking in standard Odoo | Completely missing: personal custody model, استمارة 193 Arabic form, custody transfer (نقل عهدة) between employees, custody register (كشف عهدة نموذج 1) | Custom | C12, C-INV04 | 55 | CRITICAL | No | New custody.move model + employee asset registry
INV-05 | Physical stocktake: نموذج 6 مخازن, count per item per location, variance report (كشف الزيادة والعجز), budget inclusion | stock.inventory (Odoo 17: quant adjustment) covers counting | Minor gap: نموذج 6 Arabic report, government surplus/deficit form, budget integration for revaluation | Config | — | 10 | HIGH | Partial | Configure inventory adjustment; custom Arabic report نموذج 6
INV-06 | Slow-moving stock: aging report, disposal authorization (تصريح بالبيع), committee procedure minutes | No slow-moving report in standard. Requires custom aging logic. | Missing: slow-moving stock identification by period, disposal authorization workflow, بيع أصناف committee procedure | Custom | C-INV06 | 35 | HIGH | No | Custom stock aging model + disposal workflow
INV-07 | Asset custodian insurance: government obligation to pay social insurance for عهدة holders, كشف عهد report, social insurance disbursement document | No concept in standard Odoo | Completely missing — Egyptian government-specific obligation. Track insurance liability per custodian, generate disbursement documents for social insurance office and Ministry of Labor | Custom | C-INV07 | 40 | MEDIUM | No | New government.insurance.obligation model

## 🔧 Customizations Catalog
CUSTOMIZATIONS CATALOG ¦ All Modules ¦ D365 → ODOO 17 ¦ Paradise Integrated Solutions
ID | Module | Custom Name | Requirement Source | Technical Approach | Est. Hours | Priority | Phase | Owner | Status | Linked FRD Req
C1 | Finance | CommitmentLedger | Budget commitment/encumbrance (D365 Commitment Accounting) | New model commitment.line + compute fields; hook into PO confirm/cancel; budget.line availability check on PO | 80 | CRITICAL | 5 | OD-D | Planned | —
C2 | Finance | DailyAccountingRDP | Daily accounting report (X++ RDP class equivalent) | QWeb report + custom wizard + Arabic RTL PDF layout | 40 | CRITICAL | 5 | OD-D | Planned | —
C3 | Finance | FinancialDimensions | Financial dimensions on inventory/stock transactions | Analytic distribution + custom field inheritance on stock.move lines | 60 | HIGH | 5 | OD-D | Planned | —
C4 | Finance | AgingReportArabic | D365-style AR/AP aging with configurable buckets + Arabic RTL | Inherit account.aged.partner; add bucket config wizard; Arabic RTL print | 30 | HIGH | 5 | OD-D | Planned | —
C5 | Procurement | MultiLevelPOApproval | Multi-tier PO approval by amount threshold (Egyptian gov't levels) | Custom approval.flow model linked to purchase.order; configure thresholds per org unit | 50 | CRITICAL | 5 | OD-D | Planned | PR-01
C6 | Finance | BudgetControlPO | Hard-block PO if budget line exceeded; warn on SO | Override button_confirm; budget.line check; block with Arabic error message | 45 | CRITICAL | 5 | OD-D | Planned | PR-01
C7 | Base | ArabicMenuCustom | Unified Arabic/English custom navigation menu | ir.ui.menu records + Arabic string overrides; POT/PO translation files | 20 | MEDIUM | 5 | OD-D | Planned | —
C8 | Base | BatchAutomation | Scheduled batch jobs (posting, reports, reconciliation) | ir.cron + custom batch.job model with Arabic logging and error notification | 35 | HIGH | 5 | OD-D | Planned | —
C9 | — | [EXCLUDED] | Out of scope per project decision | — | 0 | N/A | — | — | Excluded | —
C10 | Finance | ImportClearanceModule | Import clearance & customs duty tracking for gov't imports | New model customs.clearance + landed.costs integration + Arabic customs docs | 70 | HIGH | 5-6 | OD-D | Planned | —
C11 | Finance | GovernmentVendorPayment | Egyptian gov't vendor payment schedule, social insurance deductions, Ministry of Labor disbursement | Custom payment.schedule model + approval flow + gov't disbursement documents | 55 | CRITICAL | 5 | OD-D | Planned | INV-07
C12 | Inventory | AssetCustodyModule | Personal custody (عهدة) tracking: issue, transfer, register; استمارة 193 ع.ح; كشف عهدة نموذج 1 | New custody.move model + hr.employee asset registry; custody transfer wizard; Arabic print templates | 65 | CRITICAL | 5-6 | OD-D | Planned | INV-02, INV-04
C13 | Inventory | AuditTrailEnhanced | Enhanced audit trail for Egyptian gov't compliance (Financial Control Authority requirements) | Custom audit.log model; triggers on all key models; Arabic export; نموذج 9 مخازن integration | 35 | HIGH | 5 | OD-D | Planned | INV-05
C-PR01 | Procurement | GovernmentTenderLifecycle | Full government contracting lifecycle: initial ops, committee formation, tender docs, award (PR-01) | New procurement.tender model; stage workflow (draft→committee→published→evaluation→award→contract); committee minutes generator | 60 | CRITICAL | 5 | OD-D | Planned | PR-01
C-PR02 | Procurement | PublicTenderModule | Public tender (مناقصة عامة): full pipeline from RFQ to award notification, bid opening minutes, technical/financial evaluation | Extend C-PR01 with: bid.envelope model, فتح المظاريف event, البت الفني/المالي committee report, إخطار الترسية Arabic letter | 80 | CRITICAL | 5 | OD-D | Planned | PR-02
C-PR03 | Procurement | LimitedTenderExtension | Limited/local tender: pre-qualified vendor registry, sample receipt register (كشف استلام العينات), local announcement | Extend C-PR01 for limited type; add vendor.prequalification model; sample receipt form; كشف أسماء الموردين | 45 | HIGH | 5-6 | OD-D | Planned | PR-03
C-PR04 | Procurement | DirectOrderTemplates | Direct order (اتفاق مباشر): استمارة صرف 50 ع.ح, technical inspection minutes, simplified committee decision | Arabic print templates on purchase.order: استمارة 50, محضر الفحص الفني, قرار اللجنة | 30 | HIGH | 5 | OD-D | Planned | PR-04
C-PR05 | Procurement | ContractingTenderWorks | Works contracting tender: أمر إسناد, execution contract, sovereign entity flag for PR-07 | Extend C-PR01 for works type; add: subcontract.award model (أمر إسناد); entity type flag (private/sovereign); execution contract template | 70 | HIGH | 5-6 | OD-D | Planned | PR-05,PR-06,PR-07
C-PR06 | Procurement | NegotiationTender | Negotiation/practice tender (ممارسة): negotiation stage between technical and financial evaluation | Add negotiation stage to C-PR01 workflow; negotiation minutes template | 25 | MEDIUM | 5-6 | OD-D | Planned | PR-08
C-PR07 | Procurement | AuctionModule | Auction (مزايدة): inverse tender — highest bid wins; sealed envelope opening; award to highest bidder | Separate auction.lot model or tender type flag; reverse bid evaluation logic; محضر فتح المظاريف المغلقة | 35 | MEDIUM | 5-6 | OD-D | Planned | PR-09
C-INV01 | Inventory | GoodsReceiptArabicPrint | إذن إضافة Arabic print: نموذج 1 مخازن with quality inspection integration | Custom QWeb report on stock.picking; نموذج 1 layout; quality.check link; Arabic RTL | 8 | CRITICAL | 5 | OD-D | Planned | INV-01
C-INV02 | Inventory | StockIssuePermit | Stock issue permit: item type (مستديم/مستهلك), custody type (فرعية/مكانية), employee/dept assignment, إذن صرف Arabic print | Extend stock.move.line with: item_type, custody_type, employee_id fields; إذن صرف QWeb report | 45 | CRITICAL | 5 | OD-D | Planned | INV-02
C-INV03 | Inventory | ReturnPermitArabic | Return permit: نموذج 8 مخازن print, inspection committee workflow, disposal authorization | Custom QWeb نموذج 8; inspection.committee model on scrap.order; disposal sale authorization | 12 | HIGH | 5 | OD-D | Planned | INV-03
C-INV04 | Inventory | PersonalCustodyRegistry | Personal custody (عهدة شخصية): استمارة 193, custody transfer between employees, كشف عهدة نموذج 1 (part of C12) | Covered by C12 — custody.move model, استمارة 193 print, transfer wizard, نموذج 1 كشف عهدة | 0 | CRITICAL | 5 | OD-D | Covered by C12 | INV-04
C-INV05 | Inventory | StocktakeArabicReports | Physical stocktake: نموذج 6 مخازن (محضر جرد), نموذج 5 (يومية المخزن), نموذج 9 (تالف/مفقود), variance report | Custom QWeb reports on stock.inventory: نموذج 5/6/9 layouts; كشف الزيادة والعجز auto-generation | 10 | HIGH | 5 | OD-D | Planned | INV-05
C-INV06 | Inventory | SlowMovingStockModule | Slow-moving stock identification, disposal authorization (تصريح بالبيع), committee procedure minutes | Custom stock.aging model; configurable slow-moving threshold; disposal workflow with committee approval; بيع أصناف Arabic minutes | 35 | HIGH | 5-6 | OD-D | Planned | INV-06
C-INV07 | Inventory | CustodianInsuranceObligation | Gov't social insurance obligation for عهدة holders: كشف عهد, disbursement to social insurance + Ministry of Labor | New government.insurance.obligation model; liability computation per custodian; disbursement documents for التأمينات and وزارة العمل | 40 | MEDIUM | 5-6 | OD-D | Planned | INV-07
TOTAL ESTIMATED DEVELOPMENT HOURS (excluding C9 and covered items) |  |  |  |  | 1080

## ✅ UAT Scenarios
UAT SCENARIO TRACKER ¦ Procurement & Inventory ¦ الديوان العام لمحافظة بورسعيد ¦ D365 → ODOO 17
Scenario ID | Module | Scenario Name (AR) | Scenario Name (EN) | Pre-conditions | Test Steps (AR) | Expected Output / Documents | Linked Req | Priority | Result | Tester Sign-off
UAT-PR-01 | Procurement | العمليات التعاقدية الأولية | Initial Contracting Operations | مذكرة احتياج معتمدة، صلاحيات مستخدم التعاقدات | 1. فتح وحدة المشتريات 2. إنشاء مذكرة عرض الاحتياجات 3. رفع المذكرة للسلطة المختصة 4. الحصول على الموافقة 5. تحديد طريقة الطرح | قرار تشكيل اللجان، تحديد آلية الطرح (مناقصة/اتفاق مباشر/مزايدة) | PR-01 | CRITICAL | Not Run
UAT-PR-02 | Procurement | المناقصة العامة – التوريدات | Public Tender – Supplies | موافقة السلطة المختصة على المناقصة العامة، قائمة موردين معتمدين | 1. إنشاء كراسة الشروط والمواصفات 2. الإعلان العام عن المناقصة 3. استلام العطاءات (فتح المظاريف) 4. تشكيل لجنة البت الفني 5. محضر البت الفني أ ثم ب 6. محضر البت المالي 7. إخطار الترسية للمورد الفائز 8. تحرير العقد وأمر التوريد | نموذج حصر الشركات، محضر فتح المظاريف، محضر البت الفني أ/ب، محضر البت المالي 1/2، إخطار الترسية، عقد، أمر توريد، استمارة صرف | PR-02 | CRITICAL | Not Run
UAT-PR-03 | Procurement | المناقصة المحدودة – التوريدات | Limited Tender – Supplies | قائمة موردين مؤهلين مسبقاً للمناقصة المحدودة | 1. إنشاء كشف أسماء الموردين المدعوين 2. إرسال كراسة الشروط للموردين المحددين 3. استلام العينات وتسجيلها (كشف استلام العينات) 4. فحص العينات ومحضر البت الفني 5. تقييم العروض المالية 6. إخطار الترسية والتعاقد | كشف أسماء الموردين، كشف استلام العينات، محضر البت الفني، إخطار الترسية، عقد، أمر توريد | PR-03 | HIGH | Not Run
UAT-PR-04 | Procurement | الأمر المباشر – التوريدات | Direct Order – Supplies | موافقة السلطة المختصة على الاتفاق المباشر، مورد محدد | 1. إنشاء مذكرة الطرح للسلطة المختصة 2. تشكيل لجنة الفحص الفني 3. محضر الفحص الفني للعروض 4. محضر البت والترسية 5. تحرير استمارة صرف 50 ع.ح 6. إصدار أمر التوريد | استمارة صرف 50 ع.ح، محضر الفحص الفني، محضر البت، إخطار الترسية، أمر التوريد | PR-04 | HIGH | Not Run
UAT-PR-05 | Procurement | المناقصة المحدودة للمقاولات | Limited Tender – Contracting Works | مذكرة الجهة الطالبة للأعمال الإنشائية، ميزانية معتمدة | 1. استلام مذكرة الجهة الطالبة 2. إعداد كراسة الشروط والمواصفات الفنية 3. دعوة المقاولين المؤهلين 4. تقييم العروض (البت الفني والمالي) 5. إصدار أمر الإسناد 6. تحرير عقد التنفيذ | كراسة الشروط، تقرير البت الفني، تقرير البت المالي، أمر الإسناد، عقد التنفيذ | PR-05 | HIGH | Not Run
UAT-PR-06 | Procurement | الأمر المباشر للمقاولات – جهات سيادية | Direct Order – Sovereign Entities | مذكرة الجهة الطالبة، تصنيف الجهة كجهة سيادية في النظام | 1. التحقق من تصنيف الجهة كسيادية 2. إعداد مذكرة إدارة التعاقدات 3. كراسة الشروط المبسطة 4. تقرير البت الفني 5. قرار الترسية المباشر 6. أمر الإسناد وعقد التنفيذ | مذكرة إدارة التعاقدات، كراسة الشروط، تقرير البت الفني، قرار الترسية، أمر إسناد، عقد تنفيذ | PR-07 | HIGH | Not Run
UAT-PR-07 | Procurement | الطرح بالمزايدة | Auction / Competitive Bidding | قرار إجراء المزايدة، قائمة أصناف للبيع/التأجير | 1. نشر إعلان المزايدة 2. استلام العروض في مظاريف مغلقة 3. محضر فتح المظاريف المغلقة 4. ترسية العقد على أعلى سعر 5. تحرير عقد البيع/التأجير | إعلان المزايدة، محضر فتح المظاريف المغلقة، نموذج حصر العطاءات، إخطار الترسية، عقد | PR-09 | MEDIUM | Not Run
UAT-INV-01 | Inventory | إذن الإضافة – استلام المخزون | Goods Receipt / Stock Addition | أمر شراء مؤكد من إدارة المشتريات، مورد محدد، مخزن مفعّل | 1. الذهاب لأوامر الشراء > استلام 2. الضغط على إيصال استلام منتجات مبدئي > موافق 3. الضغط على محضر الفحص 4. اختيار دفعة المرجع (رقم الأمر) ومجموعة الاختبار والكمية > موافق 5. الفحص والتحقق من الصحة 6. فتح إدارة المخزون > وصول الصنف > جديد 7. اختيار إذن إضافة، المورد، رقم الأمر، الموقع، المخزن > موافق 8. إضافة سطر الصنف > ترحيل 9. طباعة إذن الإضافة (نموذج 1 مخازن) | إذن إضافة مرحّل، نموذج 1 مخازن مطبوع، تحديث رصيد المخزن | INV-01 | CRITICAL | Not Run
UAT-INV-02a | Inventory | إذن الصرف – صنف مستهلك | Stock Issue – Consumable Item | رصيد كافٍ في المخزن، طلب صرف معتمد | 1. إدارة المخزون > إدخالات دفتر اليومية > الحركة 2. جديد > اختيار اسم: إذن صرف > تأكيد نوع الدفتر > اختيار الموقع والمخزن > موافق 3. جديد > اختيار الصنف 4. اختيار نوع الصنف: مستهلك 5. اختيار الإدارة المستفيدة 6. ترحيل وطباعة إذن الصرف | إذن صرف مرحّل، خصم الكمية من رصيد المخزن، تسجيل الجهة المستفيدة | INV-02 | CRITICAL | Not Run
UAT-INV-02b | Inventory | إذن الصرف – صنف مستديم (عهدة) | Stock Issue – Durable Item (Custody) | صنف من نوع مستديم في المخزن، بيانات الموظف المستلم | 1. نفس خطوات UAT-INV-02a 2. اختيار نوع الصنف: مستديم 3. اختيار نوع العهدة: فرعية أو مكانية 4. اختيار اسم الموظف المستلم 5. ترحيل وطباعة استمارة 193 ع.ح | إذن صرف مستديم، استمارة 193 ع.ح مطبوعة، تسجيل عهدة الموظف | INV-02 | CRITICAL | Not Run
UAT-INV-03 | Inventory | إذن الارتجاع | Stock Return Permit | أصناف مراد إرجاعها، تقرير لجنة الفحص (نموذج 8 مخازن) | 1. إدارة المخزون > إدخالات دفتر اليومية > الحركة 2. جديد > اختيار نوع الدفتر: ارتجاع > تأكيد نوع الدفتر 3. اختيار الموقع والمخزن > موافق 4. جديد > اختيار الصنف المرتجع 5. ترحيل 6. طباعة نموذج 8 مخازن | إذن ارتجاع مرحّل، نموذج 8 مخازن مطبوع، تحديث رصيد المخزن | INV-03 | HIGH | Not Run
UAT-INV-04 | Inventory | العهدة الشخصية ونقل العهدة | Personal Custody & Transfer | صنف مستديم تم صرفه بعهدة موظف (من UAT-INV-02b) | 1. إدارة المخزون > العهد > عهد مخزنية 2. تحديد تاريخ تسليم العهدة 3. اختيار الموظف الجديد المستلم للعهدة 4. الضغط على نقل عهدة 5. طباعة كشف عهدة (نموذج 1 مخازن) 6. التحقق من تحديث سجل العهدة للموظف القديم والجديد | نقل عهدة مسجل، كشف عهدة (نموذج 1) لكلا الموظفين محدث، استمارة 193 ع.ح للموظف الجديد | INV-04 | CRITICAL | Not Run
UAT-INV-05 | Inventory | الجرد الدوري | Physical Stocktake | أصناف موجودة في المخزن، تفعيل وحدة الجرد | 1. إدارة المخزون > جرد > الأصناف > الجرد 2. جديد > اختيار نوع الدفتر: جرد > تأكيد > اختيار المخزن والموقع > موافق 3. تحديد كل صنف وكتابة الرقم الفعلي من واقع الجرد 4. ترحيل 5. طباعة محضر الجرد (نموذج 6 مخازن) 6. طباعة كشف الزيادة والعجز 7. طباعة يومية المخزن (نموذج 5) | محضر جرد مرحّل، نموذج 6 مخازن مطبوع، كشف الزيادة والعجز، يومية المخزن نموذج 5، تسوية الفروقات في الميزانية | INV-05 | HIGH | Not Run
UAT-INV-06 | Inventory | المخزون الراكد والتصريح بالبيع | Slow-Moving Stock & Disposal | أصناف لم يتم صرفها خلال الفترة المحددة كراكدة | 1. تشغيل تقرير المخزون الراكد بتحديد الفترة الزمنية 2. مراجعة بيان المخزون الراكد 3. رفع الطلب للجنة التصريف 4. اعتماد تصريح بالبيع من السلطة المختصة 5. إصدار محضر إجراءات بيع الأصناف 6. تسجيل البيع وتحديث المخزن | بيان مخزون راكد، تصريح بالبيع معتمد، محضر إجراءات بيع أصناف، تحديث رصيد المخزن | INV-06 | HIGH | Not Run
UAT-INV-07 | Inventory | التأمين على أرباب العهدة | Custodian Insurance Obligation | قائمة أرباب العهدة النشطين في النظام | 1. تشغيل تقرير كشف العهد لجميع الموظفين أصحاب العهدة 2. حساب التزام التأمين الاجتماعي لكل مستلم عهدة 3. إصدار مستند صرف للتأمينات الاجتماعية 4. إصدار مستند صرف لوزارة العمل فرع بورسعيد 5. ترحيل القيود المحاسبية | كشف عهد، مستند صرف التأمينات الاجتماعية، مستند صرف وزارة العمل، قيد محاسبي مرحّل | INV-07 | MEDIUM | Not Run
TOTAL SCENARIOS: 15 ¦ Procurement: 7 ¦ Inventory: 8

## 📅 Week-by-Week Plan
WEEK-BY-WEEK TASK PLAN BY ROLE ¦ D365 → ODOO 17 ¦ Procurement & Inventory ¦ Port Said Governorate
Phase | Wk | Task ID | Task / Deliverable | PM | D365-F | D365-T | OD-F | OD-D | DM | QA | CL | Status | Priority | Notes / Risks & FRD Link
PHASE 1 — INITIATION
Phase 1 | W1 | P1-01 | Kickoff: scope alignment, team roles, tools, bilingual communication plan | RA | R | C | C | C | C | I | R | In Progress | CRITICAL | Confirm Procurement (PR-01–09) and Inventory (INV-01–07) in scope
Phase 1 | W1 | P1-02 | Sign project charter; confirm Port Said Governorate stakeholders and approvers | RA | C | I | C | I | I | I | R | Not Started | CRITICAL | Key approver: الديوان العام لمحافظة بورسعيد
Phase 1 | W1 | P1-03 | Build BRD skeleton aligned to FRD structure (Procurement 9 reqs + Inventory 7 reqs) | A | R | C | C | I | I | I | C | Not Started | HIGH | Use FRD sections as BRD chapters
Phase 1 | W1 | P1-04 | Provision D365 sandbox, LCS, OData, DMF access; set up Git, DevOps board | A | C | R | I | R | I | R | R | Not Started | CRITICAL | Include access to Procurement and Inventory modules specifically
Phase 1 | W1 | P1-05 | Define change management plan for gov't users — Arabic training approach | RA | C | I | R | I | I | I | R | Not Started | HIGH | Key users: أمين المخزن, مدير إدارة التعاقدات
PHASE 2 — REVERSE ENGINEERING
Phase 2 | W2-3 | P2-01 | Process walkthrough: PR-01 العمليات التعاقدية الأولية — map full contracting lifecycle | A | R | C | C | I | I | I | R | Not Started | CRITICAL | Capture: committee formation, طريقة الطرح decision logic
Phase 2 | W2-3 | P2-02 | Process walkthrough: PR-02 المناقصة العامة — map full pipeline from RFQ to award | A | R | C | R | I | I | I | R | Not Started | CRITICAL | Capture all output documents: 10+ forms per PR-02 FRD
Phase 2 | W2-3 | P2-03 | Process walkthrough: PR-03/04 المناقصة المحدودة والأمر المباشر | A | R | C | R | I | I | I | R | Not Started | HIGH | Document: كشف استلام العينات, استمارة 50 ع.ح
Phase 2 | W3 | P2-04 | Process walkthrough: PR-05/06/07 Contracting works — private and sovereign entities | A | R | C | C | I | I | I | R | Not Started | HIGH | Identify difference in approval authority for sovereign vs private
Phase 2 | W3 | P2-05 | Process walkthrough: PR-08/09 المزايدة والممارسة — auction and negotiation tender | A | R | C | C | I | I | I | R | Not Started | MEDIUM | Lower priority; build after main tender module
Phase 2 | W3-4 | P2-06 | Process walkthrough: INV-01 إذن الإضافة — full flow from PO receipt to نموذج 1 print | A | R | C | R | I | I | I | R | Not Started | CRITICAL | Capture: محضر الفحص, quality inspection steps, نموذج 1 مخازن layout
Phase 2 | W3-4 | P2-07 | Process walkthrough: INV-02 إذن الصرف — مستديم/مستهلك, عهدة types, استمارة 193 | A | R | C | R | I | I | I | R | Not Started | CRITICAL | Capture: custody type logic (فرعية/مكانية), employee assignment
Phase 2 | W4 | P2-08 | Process walkthrough: INV-03/04 ارتجاع + عهدة شخصية — forms نموذج 8 + نقل عهدة | A | R | C | R | I | I | I | R | Not Started | HIGH | Capture: لجنة الفحص workflow, custody transfer rules
Phase 2 | W4 | P2-09 | Process walkthrough: INV-05/06/07 جرد + مخزون راكد + أرباب العهدة | A | R | C | R | I | I | I | R | Not Started | HIGH | Capture: نموذج 6 layout, disposal authorization, insurance obligation
Phase 2 | W4-5 | P2-10 | Technical RE: Export D365 schema for Procurement (purchase tables, vendor, tender customizations) | A | C | R | I | C | I | I | I | Not Started | CRITICAL | Map D365 purchase tables to Odoo purchase.* models
Phase 2 | W4-5 | P2-11 | Technical RE: Export D365 schema for Inventory (WMS tables, custody model, item type fields) | A | C | R | I | C | I | I | I | Not Started | CRITICAL | مستديم/مستهلك fields, custody tracking — no Odoo equivalent
Phase 2 | W5 | P2-12 | Collect and scan all government forms: نماذج 1,4,5,6,8,9 مخازن + استمارة 193 + استمارة 50 | A | R | C | C | I | I | I | R | Not Started | CRITICAL | Physical scan + measure Arabic RTL layout for Odoo QWeb replication
Phase 2 | W5-6 | P2-13 | Build Customizations Catalog v2.0 with all C1–C13 + C-PR01–07 + C-INV01–07 | A | R | R | R | R | I | I | C | Not Started | CRITICAL | Total custom items: 25+; estimate hours per item
Phase 2 | W5-6 | P2-14 | Produce Functional RE Report (Arabic+English); Technical RE Report; update BRD | RA | R | R | C | C | I | I | R | Not Started | HIGH | Gate to Phase 3 — client sign-off required
PHASE 3 — DATA EXTRACTION & MAPPING
Phase 3 | W6-7 | P3-01 | Extract vendor master: all vendors including gov't sovereign entities (with entity type flag) | A | C | R | I | I | R | I | C | Not Started | CRITICAL | Tag sovereign vs private vendors — impacts PR-06/07
Phase 3 | W6-7 | P3-02 | Extract item master: map مستديم/مستهلك classification, UoM, warehouse locations | A | C | R | I | I | R | I | C | Not Started | CRITICAL | مستديم/مستهلك is custom field — needs new Odoo field mapped
Phase 3 | W7 | P3-03 | Extract open POs, active contracts, and تعاقدات in-flight | A | R | C | R | I | R | I | C | Not Started | CRITICAL | Agree cut-off: any active contracts must migrate or be closed in D365
Phase 3 | W7-8 | P3-04 | Extract custody register (العهد): all employees with active عهدة, form 193 history | A | C | I | R | C | R | I | C | Not Started | CRITICAL | No standard DMF entity — may need custom OData or direct SQL
Phase 3 | W7-8 | P3-05 | Extract inventory balances per warehouse, per location, per item (with type classification) | A | C | R | R | C | R | I | C | Not Started | CRITICAL | Include slow-moving stock age data for INV-06
Phase 3 | W8 | P3-06 | Build entity mapping workbooks: vendor, item, PO, contract, inventory, custody | A | R | C | R | C | R | I | C | Not Started | CRITICAL | Custody model is new — map D365 fields to new Odoo custody.move model
Phase 3 | W8-9 | P3-07 | Define transformation rules for gov't-specific data: entity type, item type, custody type, form numbers | A | R | I | R | C | R | I | C | Not Started | HIGH | Critical for C-INV02, C12 — custody fields have no Odoo default
Phase 3 | W9 | P3-08 | Validate all mappings with client; sign-off on data cleansing log | RA | C | I | R | I | R | C | R | Not Started | CRITICAL | Client data owner must confirm custody registry completeness
PHASE 4 — GAP ANALYSIS
Phase 4 | W9 | P4-01 | Gap analysis: Procurement — D365 tender management vs Odoo 17 (PR-01 through PR-09) | A | R | C | R | C | I | I | C | Not Started | CRITICAL | Result: all 9 procurement reqs = Custom. No Odoo native tender module.
Phase 4 | W9-10 | P4-02 | Gap analysis: Inventory — D365 WMS vs Odoo 17 (INV-01 through INV-07) | A | R | C | R | C | C | I | C | Not Started | CRITICAL | INV-01/03/05 = Config. INV-02/04/06/07 = Custom.
Phase 4 | W10 | P4-03 | Finalize Customizations Catalog: 25+ items, hour estimates, priority, developer assignment | A | R | R | R | R | I | I | C | Not Started | CRITICAL | Total estimated dev hours to be confirmed with PM before Phase 5
Phase 4 | W10 | P4-04 | Client approval: scope freeze on all custom items; sign catalog | RA | C | I | C | I | I | I | R | Not Started | CRITICAL | No new requirements after this sign-off
Phase 4 | W10 | P4-05 | Produce Gap Analysis Report (Arabic primary, English reference) | A | R | C | R | I | I | I | C | Not Started | HIGH | Include government forms index with Odoo implementation approach
PHASE 5 — ODOO BUILD
Phase 5 | W10-11 | P5-01 | Install Odoo 17 staging (Docker); configure base: CoA, taxes, warehouses, locations | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Create warehouse structure matching Port Said Governorate مخازن
Phase 5 | W11 | P5-02 | Configure INV-01: stock.picking receipt + quality module; test basic GRN flow | A | I | I | R | R | I | I | C | Not Started | CRITICAL | INV-01 is Config — should work natively after setup
Phase 5 | W11 | P5-03 | Configure INV-03, INV-05: return flow and physical inventory adjustment | A | I | I | R | C | I | I | C | Not Started | HIGH | INV-03/05 = Config — configure before custom dev starts
Phase 5 | W11-12 | P5-04 | Develop C-INV01: إذن إضافة نموذج 1 مخازن Arabic QWeb print template | A | I | I | C | R | I | I | I | Not Started | CRITICAL | Must match exact physical form layout; RTL Arabic; gov't header
Phase 5 | W11-12 | P5-05 | Develop C-INV02: Stock issue permit — مستديم/مستهلك fields, custody type, استمارة 193 | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Extend stock.move.line; create إذن صرف QWeb; custody type logic
Phase 5 | W12 | P5-06 | Develop C-INV03: نموذج 8 مخازن return permit + inspection committee workflow | A | I | I | C | R | I | I | I | Not Started | HIGH | Inspection committee approval before return is posted
Phase 5 | W12-13 | P5-07 | Develop C12/C-INV04: Personal custody module — custody.move model, transfer wizard, نموذج 1 كشف عهدة | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Most complex inventory custom — start early
Phase 5 | W12-13 | P5-08 | Develop C-INV05: Stocktake Arabic reports (نموذج 5/6/9 مخازن) + variance report | A | I | I | C | R | I | I | I | Not Started | HIGH | 3 separate QWeb templates; variance auto-calculation
Phase 5 | W13 | P5-09 | Develop C-INV06: Slow-moving stock module — aging logic, disposal workflow, minutes | A | I | I | C | R | I | I | I | Not Started | HIGH | Configurable aging threshold per item category
Phase 5 | W13 | P5-10 | Develop C-INV07: Custodian insurance obligation — liability model, disbursement docs | A | I | I | C | R | I | I | I | Not Started | MEDIUM | Generate social insurance + Ministry of Labor payment docs
Phase 5 | W11-13 | P5-11 | Develop C-PR01: Government tender lifecycle module (core model + stage workflow) | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Foundation for ALL procurement customs — build first
Phase 5 | W12-14 | P5-12 | Develop C-PR02: Public tender pipeline — bid envelopes, committee minutes, award notification | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Most complex procurement custom — 10+ Arabic document templates
Phase 5 | W13-14 | P5-13 | Develop C-PR03/C-PR04: Limited tender extension + direct order Arabic print templates | A | I | C | R | R | I | I | I | Not Started | HIGH | Extend C-PR01; add sample receipt, استمارة 50 print
Phase 5 | W14 | P5-14 | Develop C-PR05: Contracting works tender — أمر إسناد, execution contract, sovereign flag | A | I | C | R | R | I | I | I | Not Started | HIGH | Sovereign entity flag critical for PR-07 different approval path
Phase 5 | W14-15 | P5-15 | Develop C-PR06/C-PR07: Negotiation tender + auction module | A | I | I | R | R | I | I | I | Not Started | MEDIUM | Lower priority — can be phased post go-live if needed
Phase 5 | W13-14 | P5-16 | Develop C5: Multi-level PO approval by amount threshold (Egyptian gov't levels) | A | I | C | R | R | I | I | I | Not Started | CRITICAL | Required for ALL procurement req approvals
Phase 5 | W14 | P5-17 | Develop C6: Budget control hard-block on PO commit vs approved budget | A | I | I | R | R | I | I | I | Not Started | CRITICAL | Arabic error message when budget exceeded
Phase 5 | W14-15 | P5-18 | QA unit testing: all custom modules (C-PR and C-INV series) | A | I | I | C | R | I | R | I | Not Started | CRITICAL | Each module: unit test + Arabic form output validation
Phase 5 | W15 | P5-19 | Client demo on staging: all 9 procurement flows + all 7 inventory flows | A | R | I | R | C | I | C | R | Not Started | HIGH | Early feedback from أمين المخزن and مدير التعاقدات key users
PHASE 6 — DATA MIGRATION & TESTING
Phase 6 | W14-15 | P6-01 | Trial load 1: vendor master, item master (with مستديم/مستهلك flags), warehouse locations | A | C | I | C | C | R | R | C | Not Started | CRITICAL | Verify custody type fields populate correctly on Odoo side
Phase 6 | W15-16 | P6-02 | Trial load 2: open POs, active contracts (التعاقدات الجارية), inventory balances | A | R | I | R | C | R | R | R | Not Started | CRITICAL | Balance reconciliation: D365 inventory value vs Odoo
Phase 6 | W15-16 | P6-03 | Trial load 3: active custody register (العهد النشطة) — all employees with عهدة | A | C | I | R | C | R | R | R | Not Started | CRITICAL | Critical for INV-04 — custody data must be 100% accurate
Phase 6 | W16 | P6-04 | UAT Cycle 1: Procurement scenarios UAT-PR-01 through UAT-PR-07 | A | R | I | R | C | I | R | R | Not Started | CRITICAL | Key user: مدير إدارة التعاقدات executes all PR scenarios
Phase 6 | W16-17 | P6-05 | UAT Cycle 1: Inventory scenarios UAT-INV-01 through UAT-INV-07 | A | R | I | R | C | C | R | R | Not Started | CRITICAL | Key user: أمين المخزن executes all INV scenarios
Phase 6 | W17 | P6-06 | Defect fix sprint: critical and high UAT defects — Arabic form issues priority | A | I | C | R | R | C | R | I | Not Started | CRITICAL | Arabic RTL form defects are highest-risk based on Phase 5 experience
Phase 6 | W17-18 | P6-07 | UAT Cycle 2: regression + re-test fixed defects + end-to-end PR→INV flow | A | R | I | R | C | C | R | R | Not Started | HIGH | Test full flow: tender (PR-02) → PO → GRN (INV-01) → issue (INV-02)
Phase 6 | W18 | P6-08 | Report validation: all government Arabic reports (نماذج 1,4,5,6,8,9 + استمارة 193) | A | R | I | R | C | R | R | R | Not Started | CRITICAL | Client finance and warehouse leads sign off on each form
Phase 6 | W18 | P6-09 | Signed UAT report; Go/No-Go meeting with الديوان العام steering committee | [8 empty] | Not Started | CRITICAL | Gate to go-live | bar: A A A A A A A A to C R R R R I R R
PHASE 7 — GO-LIVE & HYPERCARE
Phase 7 | W18-19 | P7-01 | Finalize cutover plan: Procurement (freeze تعاقدات) + Inventory (freeze إذن الإضافة/الصرف) | RA | R | R | R | R | R | R | C | Not Started | CRITICAL | Two separate freeze notifications to مشتريات and مخازن departments
Phase 7 | W19 | P7-02 | Final data extract: delta POs, delta inventory movements, delta عهدة changes | A | C | R | I | I | R | I | I | Not Started | CRITICAL | Custody delta is critical — any عهدة movements after trial load 3 must capture
Phase 7 | W19 | P7-03 | Final load to Odoo production + smoke tests: PR-01, INV-01, INV-02 transactions | A | C | I | R | C | R | R | R | Not Started | CRITICAL | Smoke test: create PO → receive → إذن إضافة → طباعة نموذج 1
Phase 7 | W19 | P7-04 | Go-Live: D365 set to read-only; Odoo production live; all users notified | [8 empty] | Not Started | CRITICAL | Arabic announcement to all staff of الديوان العام | bar: A A to I R
Phase 7 | W19-20 | P7-05 | Hypercare Week 1: on-site support at الديوان العام; monitor first real transactions | A | R | C | R | C | C | R | I | Not Started | CRITICAL | Priority: first real إذن إضافة and إذن صرف in production
Phase 7 | W20 | P7-06 | Hypercare Week 2: triage production defects; Arabic form rendering issues | A | R | C | R | R | C | R | I | Not Started | HIGH | Focus: government form print quality in production printers
Phase 7 | W20 | P7-07 | Training refreshers: أمين المخزن + مدير التعاقدات + key users; Arabic video walkthroughs | A | C | I | R | C | I | I | R | Not Started | HIGH | Produce Arabic training videos for each of the 7 inventory + 9 procurement flows
Phase 7 | W20 | P7-08 | Deliver handover package: admin guide, runbooks, Arabic user manual updates for Odoo | RA | R | R | R | R | R | R | C | Not Started | HIGH | Update User Guide Procurement (70pp) and User Guide Inventory (17pp) for Odoo
Phase 7 | W20 | P7-09 | Project close-out: lessons learned, final sign-off by الديوان العام | RA | C | I | C | I | I | I | R | Not Started | MEDIUM | Archive all FRD, FDD, UAT, and custom module documentation